## Plan
◆ ALL PROCESSES LIVE BY
Timeline: week commencing (Mon)
Process / Activity | Weeks | Start | End
★ Contract Signed
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
◆ Go-Live
★ Contract Signed
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
◆ Go-Live
★ Contract Signed
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
◆ Go-Live
Legend |  |  |  | ★ | Contract Signed | Hiring | Pre-Onboarding | Knowledge Transfer | Guided Production | ◆ | Go-Live | Today
Working days (Mon–Fri); 1 week = 5 working days. Edit dates & durations on the 'Inputs' sheet — this chart redraws automatically.

## Inputs
Plan Inputs
Edit only the YELLOW cells (blue text). Every date on the 'Plan' sheet is a formula and updates automatically.
Project name | Finance Transition Program
Client | Acme Corp
Contract signed date ★ | 2026-10-19
Pre-Onboarding (weeks) | 2
KT & Guided Production rules by vertical
Vertical | KT (weeks) | Guided Prod. (weeks)
P2P | 4 | 4
OTC | 4 | 4
RTR | 8 | 8
Source: user rule — 4 weeks for P2P & OTC, 8 weeks for RTR.
Processes
Process | Vertical | Contract signed ★ | Hiring (weeks) | Pre-Onboarding (weeks) | KT (weeks) | Guided Prod. (weeks)
Procure-to-Pay | P2P |  | 8
Order-to-Cash | OTC |  | 8
Record-to-Report | RTR |  | 10
How dates are calculated (working days Mon–Fri, holidays on the 'Holidays' sheet are skipped):
★ Contract Signed — from the table above (defaults to the project contract date).
Hiring — starts next working day after contract; 8–10 weeks standard.
Pre-Onboarding — starts next working day after hiring ends; 2 weeks.
Knowledge Transfer — after Pre-Onboarding; 4 weeks P2P/OTC, 8 weeks RTR.
Guided Production — after KT; 4 weeks P2P/OTC, 8 weeks RTR.
◆ Go-Live — next working day after Guided Production ends.
1 week = 5 working days. Pre-Onboarding / KT / Guided Prod. columns in the process table are formulas — change the rules above instead.
Note on C6: Source: user input. Default contract date for every process; override per process in the table below.
Note on C7: Rule from user: Pre-Onboarding = 2 weeks after hiring end date.

## Holidays
Holiday date | Description (optional) | Add public / client holidays in column A. They are skipped by every plan date.