## Slide 1
All processes live by 04 May 2027 — 28 weeks from contract
★ Contract signed 19 Oct 2026 · 3 processes · phased go-live by vertical
Procure-to-Pay
P2P
◆ GO-LIVE
23 Feb 2027
Tuesday · 18 weeks from contract
8w
2w
4w
4w
Hiring → Pre-Onboarding → KT → Guided Production
Order-to-Cash
OTC
◆ GO-LIVE
23 Feb 2027
Tuesday · 18 weeks from contract
8w
2w
4w
4w
Hiring → Pre-Onboarding → KT → Guided Production
Record-to-Report
RTR
◆ GO-LIVE
04 May 2027
Tuesday · 28 weeks from contract
10w
2w
8w
8w
Hiring → Pre-Onboarding → KT → Guided Production
Critical path: Record-to-Report (RTR) — 10-week hiring plus 8-week KT and 8-week Guided Production. Any slip in contract signature moves every go-live date one-for-one.
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
1
☀ Light
☾ Dark

## Slide 2
Timeline: contract to go-live by process
★ Contract signed · bars = working weeks per phase · ◆ Go-Live = next working day after Guided Production
Oct 26
Nov 26
Dec 26
Jan 27
Feb 27
Mar 27
Apr 27
May 27
Procure-to-Pay P2P
Go-Live 23 Feb 27
Hiring
8 wks
Pre-Onboarding
2 wks
Knowledge Transfer
4 wks
Guided Production
4 wks
Order-to-Cash OTC
Go-Live 23 Feb 27
Hiring
8 wks
Pre-Onboarding
2 wks
Knowledge Transfer
4 wks
Guided Production
4 wks
Record-to-Report RTR
Go-Live 04 May 27
Hiring
10 wks
Pre-Onboarding
2 wks
Knowledge Transfer
8 wks
Guided Production
8 wks
Contract Signed
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
Go-Live
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
2
☀ Light
☾ Dark

## Slide 3
Key dates and planning rules
All dates are working days; edit the Excel 'Inputs' sheet to re-plan
Process | ★ Contract | Hiring | Pre-Onboarding | Knowledge Transfer | Guided Production | ◆ Go-Live
Procure-to-Pay (P2P) | 19-Oct-26 | 20-Oct → 14-Dec (8w) | 15-Dec → 28-Dec (2w) | 29-Dec → 25-Jan (4w) | 26-Jan → 22-Feb (4w) | 23-Feb-27
Order-to-Cash (OTC) | 19-Oct-26 | 20-Oct → 14-Dec (8w) | 15-Dec → 28-Dec (2w) | 29-Dec → 25-Jan (4w) | 26-Jan → 22-Feb (4w) | 23-Feb-27
Record-to-Report (RTR) | 19-Oct-26 | 20-Oct → 28-Dec (10w) | 29-Dec → 11-Jan (2w) | 12-Jan → 08-Mar (8w) | 09-Mar → 03-May (8w) | 04-May-27
Planning rules
★ Contract Signed — project date (can be overridden per process)
Hiring — 8 to 10 weeks standard, from the next working day after contract
Pre-Onboarding — 2 weeks after hiring end date
Knowledge Transfer — P2P 4w, OTC 4w, RTR 8w
Guided Production — P2P 4w, OTC 4w, RTR 8w
◆ Go-Live — next working day after Guided Production ends
Colour key
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
3
☀ Light
☾ Dark

## Slide 4
All processes live by 04 May 2027 — 28 weeks from contract
★ Contract signed 19 Oct 2026 · 3 processes · phased go-live by vertical
Procure-to-Pay
P2P
◆ GO-LIVE
23 Feb 2027
Tuesday · 18 weeks from contract
8w
2w
4w
4w
Hiring → Pre-Onboarding → KT → Guided Production
Order-to-Cash
OTC
◆ GO-LIVE
23 Feb 2027
Tuesday · 18 weeks from contract
8w
2w
4w
4w
Hiring → Pre-Onboarding → KT → Guided Production
Record-to-Report
RTR
◆ GO-LIVE
04 May 2027
Tuesday · 28 weeks from contract
10w
2w
8w
8w
Hiring → Pre-Onboarding → KT → Guided Production
Critical path: Record-to-Report (RTR) — 10-week hiring plus 8-week KT and 8-week Guided Production. Any slip in contract signature moves every go-live date one-for-one.
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
1
☀ Light
☾ Dark

## Slide 5
Timeline: contract to go-live by process
★ Contract signed · bars = working weeks per phase · ◆ Go-Live = next working day after Guided Production
Oct 26
Nov 26
Dec 26
Jan 27
Feb 27
Mar 27
Apr 27
May 27
Procure-to-Pay P2P
Go-Live 23 Feb 27
Hiring
8 wks
Pre-Onboarding
2 wks
Knowledge Transfer
4 wks
Guided Production
4 wks
Order-to-Cash OTC
Go-Live 23 Feb 27
Hiring
8 wks
Pre-Onboarding
2 wks
Knowledge Transfer
4 wks
Guided Production
4 wks
Record-to-Report RTR
Go-Live 04 May 27
Hiring
10 wks
Pre-Onboarding
2 wks
Knowledge Transfer
8 wks
Guided Production
8 wks
Contract Signed
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
Go-Live
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
2
☀ Light
☾ Dark

## Slide 6
Key dates and planning rules
All dates are working days; edit the Excel 'Inputs' sheet to re-plan
Process | ★ Contract | Hiring | Pre-Onboarding | Knowledge Transfer | Guided Production | ◆ Go-Live
Procure-to-Pay (P2P) | 19-Oct-26 | 20-Oct → 14-Dec (8w) | 15-Dec → 28-Dec (2w) | 29-Dec → 25-Jan (4w) | 26-Jan → 22-Feb (4w) | 23-Feb-27
Order-to-Cash (OTC) | 19-Oct-26 | 20-Oct → 14-Dec (8w) | 15-Dec → 28-Dec (2w) | 29-Dec → 25-Jan (4w) | 26-Jan → 22-Feb (4w) | 23-Feb-27
Record-to-Report (RTR) | 19-Oct-26 | 20-Oct → 28-Dec (10w) | 29-Dec → 11-Jan (2w) | 12-Jan → 08-Mar (8w) | 09-Mar → 03-May (8w) | 04-May-27
Planning rules
★ Contract Signed — project date (can be overridden per process)
Hiring — 8 to 10 weeks standard, from the next working day after contract
Pre-Onboarding — 2 weeks after hiring end date
Knowledge Transfer — P2P 4w, OTC 4w, RTR 8w
Guided Production — P2P 4w, OTC 4w, RTR 8w
◆ Go-Live — next working day after Guided Production ends
Colour key
Hiring
Pre-Onboarding
Knowledge Transfer
Guided Production
Finance Transition Program | Acme Corp | Working days Mon–Fri; 1 week = 5 working days
3
☀ Light
☾ Dark